## Year 1 Rev G
JCE Infrastructure: VP527277 / MRC-2645 cost sheet Rev G (12/10/2026). JCE flies drone capture and does all GIS/register work; road imaging partner trimmed to vehicle imaging and road rating. Rates marked TBC are for Jayden to confirm.
Code | Activity (Jayden Callen) | Hours | Role | Rate | Cost ex GST | Stage | Rev F hours
A1 | Inception meeting at Moama, Council WHS induction, agenda and minutes | 14 | Dir | 200 |  | 1 | 14
A2 | Project management, partner management, monthly meetings and reports | 48 | Dir | 200 |  | 6 | 56
A3 | Document control, transmittals, monthly consultant certificates | 24 | Adm | 140 |  | 6 | 24
B1 | Pilot and calibration in Moama with partners and Council, incl. drone trial (3 days) | 24 | PE | 180 |  | 2 | 24
B2 | Council data review, segmentation, defect schema mapping (GIS set-up by technician) | 40 | Snr | 190 |  | 1 | 56
C1 | Hold point submissions incl. drone operations plan and SWMS | 36 | Snr | 190 |  | 1 | 32
C2 | Pilot review, rating guide and data template revisions | 12 | Snr | 190 |  | 2 | 12
C3 | Audit of imaging partner road data (sampled re-rates, completeness, GPS, naming) | 30 | PE | 180 |  | 4 | 60
C5 | Defect notices (condition 5 and safety) and weekly progress data | 8 | PE | 180 |  | 3 | 8
D1 | Valuation methodology review and componentisation (valuer drafts) | 8 | Snr | 190 |  | 5 | 8
D2 | Unit rates from Council contract rates and estimate data, checked against valuer benchmarks | 16 | Snr | 190 |  | 5 | 16
D3 | Useful lives and condition to remaining life relationship | 16 | Snr | 190 |  | 5 | 16
D4 | Reconciliation of valuation to the register and thresholds | 8 | PE | 180 |  | 5 | 8
D5 | Condition and remaining life sections of the valuation report | 12 | Snr | 190 |  | 5 | 12
D6 | Valuer coordination and review of valuer calculations | 12 | Dir | 200 |  | 5 | 12
E3 | Review of Level 2 bridge reports; Level 3/4 register (127 structures) | 31.75 | Dir | 200 |  | 3 | 31.75
E4 | Remaining useful life model by component and segment | 24 | Snr | 190 |  | 4 | 24
F1 | Detailed defect report (schedule compiled by technician) | 32 | Snr | 190 |  | 4 | 32
F2 | 10-year capital renewal and maintenance programs | 64 | Snr | 190 |  | 4 | 64
F3 | Inspection and condition report, draft and final | 48 | Snr | 190 |  | 4 | 48
F4 | Director QA review of all deliverables | 28 | Dir | 200 |  | 6 | 28
G1 | Guardrail and handrail safety assessment (Austroads GRD Part 6) | 32 | Snr | 190 |  | 4 | 32
G2 | Presentation of draft findings and comments register | 8 | Dir | 200 |  | 6 | 8
G3 | Close-out, data handover, return or deletion of Council data | 8 | PE | 180 |  | 6 | 8
H1 | Drone operations planning: airspace checks, CASA notifications, site risk assessments, equipment set-up | 16 | PE | 180 |  | 1 | 0
H2 | Drone capture: bridges, approaches and footbridges where the bridge partner needs imagery (about 40 structures, 7 field days) | 63 | PE | 180 |  | 3 | 0
H3 | Drone capture: rural culverts not visible in vehicle imagery (about 200), stormwater outlets, kerb and footpath hotspots, poor-access assets (9 field days) | 81 | PE | 180 |  | 3 | 0
H4 | Field travel, Gunnedah to the LGA (3 return trips) | 48 | PE | 180 |  | 3 | 0
H5 | Drone data offload, geotag check and processing (JCE share) | 21 | PE | 180 |  | 4 | 0
H6 | Check of technician first-pass ratings: kerb, footpaths, culverts, guardrail, islands, carparks, bus shelters | 15 | Snr | 190 |  | 4 | 0
H7 | Defect coding of non-road assets to Council schema (JCE share) | 20 | PE | 180 |  | 4 | 0
H8 | QA sampling: blind re-rate of 2% of JCE and partner ratings; completeness checks | 24 | PE | 180 |  | 4 | 0
H9 | GIS and asset register build, partner data integration (JCE share and review) | 30 | CAD | 160 |  | 4 | 0
Total JCE (Jayden) labour
Code | Casual labour (cost allowance + 10%) [TBC - Jayden: rates] | Hours |  | Cost rate | Amount ex GST
K1 | Casual field assistant and drone visual observer: 16 field days plus travel (192 h at $55/h cost allowance) | 192 |  | 55
K2 | Casual GIS and desktop rating technician: first-pass rating from partner and drone imagery, GIS layers, register population, image index, maps (298 h at $65/h cost allowance) | 298 |  | 65
| Equipment and travel [TBC - Jayden: rates] |  |  |  | Amount ex GST
| Drone equipment day rate (DJI Mavic 3 Enterprise with RTK, batteries, RTK corrections, processing software and storage): 17 field days at $250 per day [TBC - Jayden to confirm rate] |  |  |  | 4250
| Vehicle: 3 return trips Gunnedah to the LGA plus driving between sites, about 10,150 km at $0.96/km |  |  |  | 9744
| Accommodation: 44 room-nights at $180 (Jayden and assistant) |  |  |  | 7920
| Meals allowance: 44 person-nights at $70 |  |  |  | 3080
Item | Provisional sums (partners, until quotes due 12:00 pm Wed 28/10/2026) | Allowance |  | Mark-up | Amount ex GST
PS1 | Road imaging partner: vehicle-mounted imaging of the network (with roadside) and sealed/unsealed road rating: 1,110 km x $90 + 1,890 km x $55 + $28,000 mobilisation and outputs | 231850 |  | 0.1
PS2 | Bridge partner: Level 2, 127 structures | 117400 |  | 0.1
PS3 | Valuer: review and signed report | 30000 |  | 0.1
PS3b | Valuer: valuation calculations and benchmark unit rates | 18000 |  | 0.1
Year 1 total ex GST
Removed from Rev F: PS1 point-asset, kerb and footpath rating ($71,425), PS1 mobilisation reduced by $7,000, PS1k GIS/register $20,500 (now JCE), B3 field verification and E2 travel (replaced by drone campaigns)

## Pricing Schedule
Item | Description | Ex GST | GST | Incl GST
1 | Year 1 (2027)
2 | 2028 rolling zone year (zone share of JCE drone/GIS + partners, escalated) | 195380
3 | 2029 rolling zone year (zone share of JCE drone/GIS + partners, escalated) | 207720
4 | 2030 rolling zone year (zone share of JCE drone/GIS + partners, escalated) | 167500
5 | 2031 rolling zone year (zone share of JCE drone/GIS + partners, escalated) | 254390
LUMP SUM (Schedule 1)
Opt | Level 3/4 bridge inspection, per bridge | 7400 | 740 | 8140

## Category Split
Asset category | Year 1 ex GST
Sealed roads (urban, regional, local) | 173736.12
Unsealed roads | 180779.47
Kerb and gutter | 9182.45
Footpaths and cycleways | 23147.42
Roundabouts, traffic islands and medians | 6495.54
Carparks | 13147.6
Rural culverts | 48677.42
Guardrail | 21738.75
Bus shelters | 1826.06
Bridges and major culverts | 171127.47
Footbridges | 12173.7
Total

## Jayden Hours Profile
Month | Jayden hours | Working weeks | Hours per week | Casual hours (assistant + technician)
Dec 2026 | 70 | 2 |  | 0
Jan 2027 | 108 | 3 |  | 20
Feb 2027 | 145 | 4 |  | 140
Mar 2027 | 158 | 4.4 |  | 170
Apr 2027 | 140 | 4 |  | 80
May 2027 | 160 | 4.4 |  | 60
Jun 2027 | 121 | 3.6 |  | 20
Total