## CQA Engineer
CQA Engineer
PROJECT: | Gregadoo WMC CQA Engineer - New General Waste Cell 3.1 & Monocell M1.1 (RFT CT2027005)
LOCATION: | 162 Ashfords Road, Gregadoo NSW 2650
PLAN REGISTRATION: | N/A (CQA services)
PREPARED BY: | JCE Infrastructure Pty Ltd (ABN 29 699 165 663) - Jayden Callen, Director
BOQ REVISION: | F (final for lodgement; partner provisional sums to be replaced by quoted prices before lodgement)
DATE: | 12/10/2026
ITEM | DESCRIPTION | QTY | Lead CQA Engineer (J. Callen) | Director review & certification | Project engineer / admin / travel | UNIT | RATE | COST (ex GST)
|  |  | Rate ($/hr) | Rate ($/hr) | Rate ($/hr)
|  |  | 190 | 200 | 180
|  |  | Hours | Hours | Hours
Portion 1 - General Cell 3.1
1 | Preliminaies & Overheads
1.1 | Site Establishment, including site management, travel, disbursements, and all other project overheads and management plans | 1 | 100 | 8 | 160 | Item | 49400 | 49400
JCE: management plans, CQA Implementation Plan, submittal/MQA review, inductions, partner coordination, fortnightly meetings, monthly reports and claims; project engineer hours include travel time for 8 return trips Gunnedah - Wagga Wagga (120 h).
1.1a | Disbursements (added line): vehicle 8 x 1,260 km at $0.96/km, accommodation and meals 22 nights at $280 | 1 |  |  |  | Item | 15836.8 | 15836.8
2 | Coordination of works and results, compilation of records as required to achieve compliance for the works. Includes: coordination with the Superintendent, materials and quality records, as-constructed reports, and ITP & QA review.
2.1 | Earthworks and Site Preparation | 1 | 22 |  |  | Item | 4180 | 4180
2.2 | Groundwater Relief System | 1 | 22 |  |  | Item | 4180 | 4180
2.3 | Engineered Fill Layer | 1 | 40 | 2 |  | Item | 8000 | 8000
2.4 | Anchor Trenches | 1 | 6 |  |  | Item | 1140 | 1140
2.5 | Geosynthetic Clay Layer | 1 | 32 |  |  | Item | 6080 | 6080
2.6 | HDPE Liner | 1 | 64 | 4 |  | Item | 12960 | 12960
2.7 | Cushion Geotextile | 1 | 16 |  |  | Item | 3040 | 3040
2.8 | Leachate Collection System | 1 | 20 |  |  | Item | 3800 | 3800
2.9 | Gravel Drainage Layer | 1 | 30 | 2 |  | Item | 6100 | 6100
2.10 | Separation Geotextile | 1 | 6 |  |  | Item | 1140 | 1140
2.11 | Drainage Geocomposite | 1 | 6 |  |  | Item | 1140 | 1140
2.12 | Woven Geotextile | 1 | 4 |  |  | Item | 760 | 760
2.13 | Fencing | 1 | 4 |  |  | Item | 760 | 760
2.14 | Leachate and Groundwater Transfer Systems | 1 | 10 |  |  | Item | 1900 | 1900
JCE hours in items 2.x cover 14 site days by J. Callen at critical hold points plus review of daily logs, test results and hold point packages. Resident technician time is in provisional sums 2.PS1 and 2.PS2 below.
3 | Compile, prepare and submit final report for EPA approval. | 1 | 60 | 12 | 16 | Item | 16680 | 16680
Prepared and signed by JCE (CQA Engineer of record), reviewed and co-signed by the partner's senior landfill CQA engineer (PS3).
3A | Provisional sums (added lines) - partner and specialist services, each including JCE's 10% coordination margin; claimed only to the extent used
3.PS1 | Partner resident CQA technician(s): full-time attendance during the geosynthetic lining works and at hold points (CQA Plans) | 60 |  |  |  | day | 1430 | 85800
3.PS2 | Partner resident CQA technician(s): attendance during all other working hours of the works (Part D 1.13) | 85 |  |  |  | day | 1430 | 121550
3.PS3 | Partner senior landfill CQA engineer: plan and records review, liner start-up attendance, technical advice, co-signing of the CQA report | 1 |  |  |  | Item | 13200 | 13200
3.PS4 | NATA IQA testing of soils and gravels, including sample transport (Wagga laboratory) | 1 |  |  |  | Item | 13200 | 13200
3.PS5 | NATA IQA testing of geosynthetics (GCL, HDPE, geotextiles, geocomposite) | 1 |  |  |  | Item | 30800 | 30800
3.PS6 | Liner integrity (electrical leak location) surveys, exposed liner and after the gravel drainage layer (subject to RFI 2) | 1 |  |  |  | Item | 41800 | 41800
3.PS7 | Independent check survey of Planes 1 to 3 | 1 |  |  |  | Item | 6600 | 6600
4 | Hourly rate for variations (nominate for each staff member and any disbursements)
4.1 | Lead CQA Engineer (J. Callen) $190/hr; site day (10 h) $1,900; Director review & certification $200/hr; Project engineer/admin/travel $180/hr |  |  |  |  | hr | 190
4.2 | Partner resident CQA technician $1,430/day (10 h, incl. 10% margin; allowance TBC from quote). Accommodation & meals $280/night, vehicle $0.96/km; sub-consultants & laboratory testing at cost + 10% |  |  |  |  | day | 1430
[7 empty] | Subtotal = | 450046.8
Portion 2 - Monocell M1.1
5 | Preliminaies & Overheads
5.1 | Site Establishment, including site management, travel, disbursements, and all other project overheads and management plans | 1 | 50 | 4 | 95 | Item | 27400 | 27400
JCE: management plans, CQA Implementation Plan, submittal/MQA review, inductions, partner coordination, fortnightly meetings, monthly reports and claims; project engineer hours include travel time for 5 return trips Gunnedah - Wagga Wagga (75 h).
5.1a | Disbursements (added line): vehicle 5 x 1,260 km at $0.96/km, accommodation and meals 13 nights at $280 | 1 |  |  |  | Item | 9688 | 9688
6 | Coordination of works and results, compilation of records as required to achieve compliance for the works. Includes: coordination with the Superintendent, materials and quality records, as-constructed reports, and ITP & QA review.
6.1 | Earthworks and Site Preparation | 1 | 13 |  |  | Item | 2470 | 2470
6.2 | Groundwater Relief System | 1 | 13 |  |  | Item | 2470 | 2470
6.3 | Engineered Fill Layer | 1 | 22 | 1 |  | Item | 4380 | 4380
6.4 | Anchor Trenches | 1 | 4 |  |  | Item | 760 | 760
6.5 | Geosynthetic Clay Layer | 1 | 18 |  |  | Item | 3420 | 3420
6.6 | HDPE Liner | 1 | 46 | 3 |  | Item | 9340 | 9340
6.7 | Cushion Geotextile | 1 | 4 |  |  | Item | 760 | 760
6.8 | Leachate Collection System | 1 | 16 |  |  | Item | 3040 | 3040
6.9 | Gravel Drainage Layer | 1 | 16 | 1 |  | Item | 3240 | 3240
6.10 | Separation Geotextile | 1 | 4 |  |  | Item | 760 | 760
6.11 | Drainage Geocomposite | 1 | 4 |  |  | Item | 760 | 760
6.12 | Woven Geotextile | 1 | 3 |  |  | Item | 570 | 570
6.13 | Fencing | 1 | 3 |  |  | Item | 570 | 570
6.14 | Leachate and Groundwater Transfer Systems | 1 | 6 |  |  | Item | 1140 | 1140
JCE hours in items 6.x cover 8 site days by J. Callen at critical hold points plus review of daily logs, test results and hold point packages. Resident technician time is in provisional sums 6.PS1 and 6.PS2 below.
7 | Compile, prepare and submit final report for EPA approval. | 1 | 40 | 8 | 10 | Item | 11000 | 11000
Prepared and signed by JCE (CQA Engineer of record), reviewed and co-signed by the partner's senior landfill CQA engineer (PS3).
7A | Provisional sums (added lines) - partner and specialist services, each including JCE's 10% coordination margin; claimed only to the extent used
7.PS1 | Partner resident CQA technician(s): full-time attendance during the geosynthetic lining works and at hold points (CQA Plans) | 30 |  |  |  | day | 1430 | 42900
7.PS2 | Partner resident CQA technician(s): attendance during all other working hours of the works (Part D 1.13) | 50 |  |  |  | day | 1430 | 71500
7.PS3 | Partner senior landfill CQA engineer: plan and records review, liner start-up attendance, technical advice, co-signing of the CQA report | 1 |  |  |  | Item | 7700 | 7700
7.PS4 | NATA IQA testing of soils and gravels, including sample transport (Wagga laboratory) | 1 |  |  |  | Item | 6600 | 6600
7.PS5 | NATA IQA testing of geosynthetics (GCL, HDPE, geotextiles, geocomposite) | 1 |  |  |  | Item | 15400 | 15400
7.PS6 | Liner integrity (electrical leak location) surveys, exposed liner and after the gravel drainage layer (subject to RFI 2) | 1 |  |  |  | Item | 17600 | 17600
7.PS7 | Independent check survey of Planes 1 to 3 | 1 |  |  |  | Item | 3300 | 3300
8 | Hourly rate for variations (nominate for each staff member and any disbursements)
8.1 | Lead CQA Engineer (J. Callen) $190/hr; site day (10 h) $1,900; Director review & certification $200/hr; Project engineer/admin/travel $180/hr |  |  |  |  | hr | 190
8.2 | Partner resident CQA technician $1,430/day (10 h, incl. 10% margin; allowance TBC from quote). Accommodation & meals $280/night, vehicle $0.96/km; sub-consultants & laboratory testing at cost + 10% |  |  |  |  | day | 1430
[7 empty] | Subtotal = | 246768
[7 empty] | TOTAL (EX GST) | 696814.8
[7 empty] | GST | 69681.48
[7 empty] | TOTAL (INCL GST) | 766496.28
Notes: Travel, accommodation and all disbursements are included (Annexure Item 9). Provisional sums PS1 to PS7 are allowances for the Riverina CQA partner and specialists and are claimed only to the extent used at the rates shown; PS2 is the cost of full-time presence outside the lining works under Part D 1.13 (RFI 1). GITA Level 1 testing and GTA testing are excluded (RFI 2).