## Labour Y1
JCE Infrastructure: VP527277 / MRC-2645 cost sheet Rev F (12/10/2026). Year 1 JCE labour, all delivered by Jayden Callen; role codes set the charge rate only.
Code | Activity | Hours | Role | Rate | Cost ex GST | Stage | Draft Rev A hours
A1 | Inception meeting at Moama, Council WHS induction, agenda and minutes | 14 | Dir | 200 |  | 1 | 14
A2 | Project management, partner management, monthly meetings and reports, Dec 2026 to Jun 2027 | 56 | Dir | 200 |  | 6 | 56
A3 | Document control, transmittals, monthly consultant certificates, data handover | 24 | Adm | 140 |  | 6 | 24
B1 | Pilot and calibration in Moama with partners and Council (3 days on site) | 24 | PE | 180 |  | 2 | 24
B2 | Council data review, segmentation set-up, defect schema mapping | 56 | Snr | 190 |  | 1 | 56
B3 | Field verification and partner QA audits (2 visits x 3 days) | 48 | PE | 180 |  | 3 | 48
C1 | Hold point submissions: methodology, program, providers, SWMS and safety plans | 32 | Snr | 190 |  | 1 | 32
C2 | Pilot review, rating guide and data template revisions | 12 | Snr | 190 |  | 2 | 12
C3 | Data QA audit of partner data against Council template (sampled re-rates, completeness, GPS, naming) | 60 | PE | 180 |  | 4 | 100
C4 | Merge partner GIS layers and data into one register; check Asset IDs and metadata | 24 | CAD | 160 |  | 4 | 80
C5 | Review of partner defect notices and weekly progress data | 8 | PE | 180 |  | 3 | 16
D1 | Valuation methodology review and componentisation (valuer drafts) | 8 | Snr | 190 |  | 5 | 16
D2 | Unit rates: Council contract rates and estimate data, checked against valuer benchmarks | 16 | Snr | 190 |  | 5 | 32
D3 | Useful lives and condition to remaining life relationship by component | 16 | Snr | 190 |  | 5 | 24
D4 | Reconciliation of valuation to the register and capitalisation thresholds | 8 | PE | 180 |  | 5 | 72
D5 | Condition and remaining life sections of the valuation report | 12 | Snr | 190 |  | 5 | 28
D6 | Valuer coordination and review of the valuer calculations | 12 | Dir | 200 |  | 5 | 8
E1 | Condition and defect maps by zone and asset class (from partner GIS) | 12 | CAD | 160 |  | 4 | 24
E2 | Travel time, Gunnedah to Moama and the four zones (three return trips) | 48 | PE | 180 |  | 3 | 48
E3 | Review of Level 2 bridge reports; Level 3/4 recommendations register (127 structures) | 31.75 | Dir | 200 |  | 3 | 31.75
E4 | Remaining useful life model by component and segment; explanation of changes | 24 | Snr | 190 |  | 4 | 24
F1 | Detailed defect report from the partner defect schedule | 32 | Snr | 190 |  | 4 | 48
F2 | 10-year capital renewal and maintenance programs | 64 | Snr | 190 |  | 4 | 64
F3 | Inspection and condition report, draft and final | 48 | Snr | 190 |  | 4 | 48
F4 | Director QA review of all deliverables | 28 | Dir | 200 |  | 6 | 28
G1 | Guardrail and handrail safety assessment (Austroads GRD Part 6) | 32 | Snr | 190 |  | 4 | 32
G2 | Presentation of draft findings (online) and comments register | 8 | Dir | 200 |  | 6 | 8
G3 | Close-out, data handover, return or deletion of Council data | 8 | PE | 180 |  | 6 | 8
Total JCE labour
| Disbursements (vehicle 6,300 km x $0.96; 12 nights x $180) |  |  |  | 8208
Item | Provisional sums (partner allowances until quotes due 12:00 pm Wed 28/10/2026) | Allowance |  | Mark-up | Amount ex GST
PS1 | Road imaging partner: imaging, inventory, condition data (as Rev A) | 310275 |  | 0.1
PS1k | Road imaging partner: GIS layers, register in Council template, coded defect schedule (moved from JCE hours) | 20500 |  | 0.1
PS2 | Bridge partner: Level 2, 127 structures (as Rev A) | 117400 |  | 0.1
PS3 | Valuer: review and signed report (as Rev A) | 30000 |  | 0.1
PS3b | Valuer: valuation calculations and benchmark unit rates (moved from JCE hours; matches RFQ ALT price) | 18000 |  | 0.1
Year 1 total ex GST

## Pricing Schedule
Item | Description | Ex GST | GST | Incl GST
1 | Year 1 (2027) comprehensive inspection and valuation
2 | 2028 rolling zone year | 188950
3 | 2029 rolling zone year | 200570
4 | 2030 rolling zone year | 163310
5 | 2031 rolling zone year | 247000
LUMP SUM (Schedule 1)
Opt | Level 3/4 bridge inspection, per bridge | 7400 | 740 | 8140

## Category Split
Asset category | Year 1 ex GST
Sealed roads (urban, regional, local) | 182826.24
Unsealed roads | 190238.13
Kerb and gutter | 9662.89
Footpaths and cycleways | 24358.53
Roundabouts, traffic islands and medians | 6835.4
Carparks | 13835.5
Rural culverts | 51224.29
Guardrail | 22876.16
Bus shelters | 1921.6
Bridges and major culverts | 180081.11
Footbridges | 12810.65
Total

## JCE Hours Profile
Month | JCE hours (approx.) | Hours per week
Dec 2026 | 60
Jan 2027 | 90
Feb 2027 | 110
Mar 2027 | 120
Apr 2027 | 95
May 2027 | 165
Jun 2027 | 125
Total