## Schedule C
SCHEDULE C- BREAKDOWN OF LUMP SUM
Newstead Levee Design
LOCATION: Newstead, Victoria
M2025-125
CLIENT: Mount Alexander Shire Council
| Version |  |  | 1
Schedule C (ALTERNATIVE A, full scope: for Schedule K comparison only, not the tender amount)
ITEM | DELIVERABLES OUTLINED WITHIN THE PROJECT BRIEF |  |  | $ AMOUNT (exc GST)
1 | General Items
1.1 | Project inception and available information and reference document review Confirm information gaps and prepare a Design Basis Memorandum. |  |  | 14810
1.2 | Design Basis Memorandum Council review and acceptance of investigation requirements and approval pathway. |  |  | 24410
1.3 | Concept alignment and hydraulic impact review Council review of alignment options, flood impacts, fill volume, property impacts, approval risks and recommended concept. |  |  | 80030
1.4 | 50% design review Council review of concept design plans, cost estimates and risk register. |  |  | 34400
1.5 | 80% design review Council review of detailed design plans, cost estimates and risk register. |  |  | 32750
1.6 | Final design / Issued for Tender package Council acceptance of final drawings, specification, quantities, cost estimate, design report, approvals summary and design certification. |  |  | 50820
2 | Provisional Quantity Items | Unit | Rate
2.1 | Additional ground survey works required as part of the information gap works, including all field works and associated data preparation. | Day | [TBC - Jayden: $ per day, surveyor rate + 10%]
3 | Value Add Options
3.1 | See JCE proposal Section 10.3 (Alternative A, full scope)
3.2
Sub Total (Exc. GST)
GST Component (10%)
Total Tender Amount (Inc. GST)
CONSULTANT DETAILS
Name of Consultant: | JCE Infrastructure Pty Ltd (ABN 29 699 165 663)
Address of Consultant: | [TBC - Jayden: JCE business address]
Signed: | [signature]
Print Name: | Jayden Callen, Director