## Year 1 Rev H
JCE Infrastructure: VP527277 / MRC-2645 cost sheet Rev H, Our ref FP-022 (12/10/2026; rig $550/day cost basis, Year 1 capture/rating margin add-back $74,900 in the technician rate ($160 vs $110 cost basis) and capture day rate ($1,850 vs $550)). JCE does vehicle road imaging and rating, drone capture and all GIS/register work in-house; no road imaging partner. Rates marked TBC are for Jayden to confirm.
Code | Activity (Jayden Callen) | Hours | Role | Rate | Cost ex GST | Stage | Rev G hours
A1 | Inception meeting at Moama, Council WHS induction, agenda and minutes | 14 | Dir | 200 |  | 1 | 14
A2 | Project management, partner management, monthly meetings and reports | 48 | Dir | 200 |  | 6 | 48
A3 | Document control, transmittals, monthly consultant certificates | 24 | Adm | 140 |  | 6 | 24
B1 | Pilot and calibration in Moama with partners and Council, incl. drone trial (3 days) | 24 | PE | 180 |  | 2 | 24
B2 | Council data review, segmentation, defect schema mapping (GIS set-up by technician) | 40 | Snr | 190 |  | 1 | 40
C1 | Hold point submissions incl. drone operations plan and SWMS | 36 | Snr | 190 |  | 1 | 36
C2 | Pilot review, rating guide and data template revisions | 12 | Snr | 190 |  | 2 | 12
C5 | Defect notices (condition 5 and safety) and weekly progress data | 8 | PE | 180 |  | 3 | 8
D1 | Valuation methodology review and componentisation (valuer drafts) | 8 | Snr | 190 |  | 5 | 8
D2 | Unit rates from Council contract rates and estimate data, checked against valuer benchmarks | 16 | Snr | 190 |  | 5 | 16
D3 | Useful lives and condition to remaining life relationship | 16 | Snr | 190 |  | 5 | 16
D4 | Reconciliation of valuation to the register and thresholds | 8 | PE | 180 |  | 5 | 8
D5 | Condition and remaining life sections of the valuation report | 12 | Snr | 190 |  | 5 | 12
D6 | Valuer coordination and review of valuer calculations | 12 | Dir | 200 |  | 5 | 12
E3 | Review of Level 2 bridge reports; Level 3/4 register (127 structures) | 31.75 | Dir | 200 |  | 3 | 31.75
E4 | Remaining useful life model by component and segment | 24 | Snr | 190 |  | 4 | 24
F1 | Detailed defect report (schedule compiled by technician) | 32 | Snr | 190 |  | 4 | 32
F2 | 10-year capital renewal and maintenance programs (spreadsheets built by technician) | 56 | Snr | 190 |  | 4 | 64
F3 | Inspection and condition report, draft and final (tables by technician) | 40 | Snr | 190 |  | 4 | 48
F4 | Director QA review of all deliverables | 28 | Dir | 200 |  | 6 | 28
G1 | Guardrail and handrail safety assessment (Austroads GRD Part 6) | 28 | Snr | 190 |  | 4 | 32
G2 | Presentation of draft findings and comments register | 8 | Dir | 200 |  | 6 | 8
G3 | Close-out, data handover, return or deletion of Council data | 8 | PE | 180 |  | 6 | 8
H1 | Drone operations planning: airspace checks, CASA notifications, site risk assessments, equipment set-up | 12 | PE | 180 |  | 1 | 16
H2 | Drone capture: bridges, approaches and footbridges where the bridge partner needs imagery (about 40 structures, 7 field days) | 63 | PE | 180 |  | 3 | 63
H3 | Drone capture: rural culverts not visible in vehicle imagery (about 200), stormwater outlets, kerb and footpath hotspots, poor-access assets (9 field days) | 81 | PE | 180 |  | 3 | 81
H4 | Field travel, Gunnedah to the LGA (3 return trips) | 48 | PE | 180 |  | 3 | 48
H5 | Drone data offload, geotag check and processing (JCE share) | 21 | PE | 180 |  | 4 | 21
H6 | Check of technician first-pass ratings: kerb, footpaths, culverts, guardrail, islands, carparks, bus shelters | 15 | Snr | 190 |  | 4 | 15
H7 | Defect coding of non-road assets to Council schema (JCE share) | 20 | PE | 180 |  | 4 | 20
H8 | QA sampling: blind re-rate of 2% of non-road ratings; completeness checks | 24 | PE | 180 |  | 4 | 24
H9 | GIS and asset register build, partner data integration (JCE share and review) | 20 | CAD | 160 |  | 4 | 30
R1 | Vehicle capture rig set-up, calibration, test runs, capture methodology and SWMS | 16 | PE | 180 |  | 1 | 0
R2 | Ride-along supervision of vehicle capture (2 days) | 20 | PE | 180 |  | 3 | 0
R3 | Daily remote QC of uploaded imagery (about 27 capture days) | 13 | PE | 180 |  | 3 | 0
R4 | Road condition rating QA: blind re-rate of 2% of road segments, check of technician road ratings and road defects | 30 | Snr | 190 |  | 4 | 0
R5 | Image naming, GNSS track and image index scripts | 8 | PE | 180 |  | 4 | 0
Total JCE (Jayden) labour
Code | Casual labour (charge rates; K1 fixed allowance) [TBC - Jayden: rates] | Hours or 1 |  | Rate | Amount ex GST
K1 | Casual driver and field assistant: about 30 capture days including the pilot, contingency days, drone visual observer days, data offload and travel (fixed allowance, paid at or above award) | 1 |  | 18000
K2 | Casual GIS and desktop rating technician: first-pass rating of about 300,000 road and roadside images and drone imagery, road defect coding, image processing, GIS layers, register population, image index, maps and report tables (718 h at the JCE CAD / GIS Technician rate of $160/h) | 718 |  | 160
| Equipment, travel and associate certifying engineer [TBC - Jayden: rates] |  |  |  | Amount ex GST
| Drone equipment day rate (DJI Mavic 3 Enterprise with RTK, batteries, RTK corrections, processing software and storage): 17 field days at $250 per day [TBC - Jayden to confirm rate] |  |  |  | 4250
| Vehicle capture day rate (Mosaic 51/X-class 360 rig with Emlid RS3 RTK GNSS, vehicle fit-out, data storage and image processing): 30 capture and pilot days at $1,850 per day |  |  |  | 55500
| Rating and image review software allowance, including AI-assisted pre-rating if used [TBC - Jayden] |  |  |  | 3000
| Vehicle: 3 return trips Gunnedah to the LGA, drone site driving and about 4,800 km of capture driving and repositioning, about 14,950 km at $0.96/km [TBC - Jayden to confirm rate] |  |  |  | 14352
| Accommodation: 64 room-nights at $180 (Jayden and assistant) |  |  |  | 11520
| Meals allowance: 64 person-nights at $70 |  |  |  | 4480
| Associate certifying engineer (Sunny Lotay, Lotay Civil): independent technical review and certification of JCE reports, 24 h at $220/h allowance (cost plus 10%) [TBC - Jayden to confirm rate] |  |  |  | 5808
| Rig backup: budget 360 camera with RTK logger carried as a spare, or short-term hire of a second rig if capture falls more than a week behind |  |  |  | 5000
Item | Provisional sums (partners, until quotes due 12:00 pm Wed 28/10/2026) | Allowance |  | Mark-up | Amount ex GST
PS2 | Bridge partner: Level 2, 127 structures | 117400 |  | 0.1
PS3 | Valuer: review and signed report | 30000 |  | 0.1
PS3b | Valuer: valuation calculations and benchmark unit rates | 18000 |  | 0.1
Year 1 total ex GST
Removed from Rev G: PS1 road imaging partner ($231,850 allowance, $255,035 with mark-up) and C3 partner data audit; added JCE vehicle capture (rig day rate, driver, technician rating, capture km, nights, rig backup)

## Pricing Schedule
Item | Description | Ex GST | GST | Incl GST
1 | Year 1 (2027)
2 | 2028 rolling zone year (zone share of JCE capture, drone and GIS + partners, escalated) | 156670
3 | 2029 rolling zone year (zone share of JCE capture, drone and GIS + partners, escalated) | 165360
4 | 2030 rolling zone year (zone share of JCE capture, drone and GIS + partners, escalated) | 140990
5 | 2031 rolling zone year (zone share of JCE capture, drone and GIS + partners, escalated) | 210440
LUMP SUM (Schedule 1)
Opt | Level 3/4 bridge inspection, per bridge | 7400 | 740 | 8140

## Category Split
Asset category | Year 1 ex GST
Sealed roads (urban, regional, local) | 154914.21
Unsealed roads | 161194.52
Kerb and gutter | 8187.66
Footpaths and cycleways | 20639.72
Roundabouts, traffic islands and medians | 5791.84
Carparks | 11723.24
Rural culverts | 43403.89
Guardrail | 19383.66
Bus shelters | 1628.23
Bridges and major culverts | 152588.18
Footbridges | 10854.85
Total

## Jayden Hours Profile
Month | Jayden hours | Working weeks | Hours per week | Casual hours (assistant + technician)
Dec 2026 | 74 | 2 |  | 10
Jan 2027 | 112 | 3 |  | 50
Feb 2027 | 150 | 4 |  | 230
Mar 2027 | 161 | 4.4 |  | 260
Apr 2027 | 146 | 4 |  | 230
May 2027 | 160 | 4.4 |  | 120
Jun 2027 | 122 | 3.6 |  | 40
Total