## Outreach list
Priority | Bid | Discipline/role | Firm | Contact name | Email | Phone | What to send | Quote/reply due | Status | Notes
1 | TN-1640786, BUYNSW-T026-2026, VP527277, VP527819, VP527574, VP527224, VP523438, VP527469 | Referee: RAAF Base Townsville (Defence delivery, Jayden with SCP Consulting for CPB). Ask consent, title, phone, year, value, role, Defence limits | CPB Contractors | Maverick Parker | Maverick.Parker@cpbcon.com.au |  | Referee_Consent_Form: /home/user/JCE/Outreach/forms/Referee_Consent_Form.pdf (email template in EMAIL_TEMPLATES.md) | Reply by Thu 15/10/2026 (earliest lodgement: TN-1640786 lodge by 16/10) |  | FPs and checklists print 'Maverick Partner': correct to 'Maverick Parker' (or as he confirms) in every FP before lodging
1 | TN-1640786, BUYNSW-T026-2026, VP523438, VP527224, VP527469, VP527574 | Referee: Named referee (Jayden's director 03/2025 to 05/2026). Confirm he knows about these tenders and is available | Langtree Consulting Engineers | Brett Langtree | brett@langtreeconsulting.com.au | 0400 699 979 | Referee_Consent_Form: /home/user/JCE/Outreach/forms/Referee_Consent_Form.pdf (email template in EMAIL_TEMPLATES.md) | Reply by Thu 15/10/2026 (earliest lodgement: TN-1640786 lodge by 16/10) |  | Details already printed in FPs; consent form optional, quick call is enough
1 | TN-1640786, BUYNSW-T026-2026, VP523438, VP527224, VP527469, VP527574, VP527819 | Referee: Named referee and independent peer reviewer. Confirm availability, years of experience, referee for Triton / HMAS Watson | SCP Consulting | Livio Chiarot FIEAust | livio.chiarot@scpconsult.com.au | 0418 150 028 | Referee_Consent_Form: /home/user/JCE/Outreach/forms/Referee_Consent_Form.pdf (email template in EMAIL_TEMPLATES.md) | Reply by Thu 15/10/2026 (earliest lodgement: TN-1640786 lodge by 16/10) |  | Also confirm availability for 4 weeks after 04/11 (BUYNSW)
1 | TN-1640786, BUYNSW-T026-2026, VP527277, VP527819, VP527574, VP527224, VP523438, VP527469 | Referee: Ravenshoe leachate storage facility and floodway rectification (Jayden at Langtree Consulting). Ask consent, title, phone, email | Tablelands Regional Council | Darren Quilliam | TBC - phone |  | Referee_Consent_Form: /home/user/JCE/Outreach/forms/Referee_Consent_Form.pdf (email template in EMAIL_TEMPLATES.md) | Reply by Thu 15/10/2026 (earliest lodgement: TN-1640786 lodge by 16/10) |  | Get his number from Tablelands Regional Council switchboard or Jayden's Langtree records
1 | VP527224 | Economics and engagement (VP527224) | AEC Group (Townsville) |  | TBC - phone |  | [VP527224 Economics_and_Engagement] RFQ: /home/user/JCE/FP/VP527224/Economics_and_Engagement/JCE_RFQ_Economics_and_Engagement_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Economics_and_Engagement.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Economics and Engagement: 12:00 pm AEST Thu 15/10/2026
1 | TN-1640786 | Town planning (contributions planning) (TN-1640786) | All About Planning (Port Macquarie) | Michelle (cc Peter) | michelle@allaboutplanning.com.au; cc peter@allaboutplanning.com.au |  | [TN-1640786 Town_Planning] RFQ: /home/user/JCE/FP/TN-1640786/Town_Planning/JCE_RFQ_Town_Planning_Mid-Western-Contributions-Plan_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_TN-1640786_Town_Planning.pdf | TN-1640786 Town Planning: 12:00 pm Thu 15/10/2026
1 | VP527224 | Marine and coastal engineering (VP527224) | BMT (Brisbane) |  | TBC - phone |  | [VP527224 Marine_and_Coastal_Engineering] RFQ: /home/user/JCE/FP/VP527224/Marine_and_Coastal_Engineering/JCE_RFQ_Marine_and_Coastal_Engineering_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Marine_and_Coastal_Engineering.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Marine and Coastal Engineering: 12:00 pm AEST Thu 15/10/2026
1 | TN-1640786 | Town planning (contributions planning) (TN-1640786) | Bartlett Planning Solutions (Tamworth) | Nathan Bartlett | nathan@bartlettplanning.com.au |  | [TN-1640786 Town_Planning] RFQ: /home/user/JCE/FP/TN-1640786/Town_Planning/JCE_RFQ_Town_Planning_Mid-Western-Contributions-Plan_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_TN-1640786_Town_Planning.pdf | TN-1640786 Town Planning: 12:00 pm Thu 15/10/2026
1 | VP527224 | Cost planning (VP527224) | Beacon Consulting (QLD) |  | TBC - phone |  | [VP527224 Cost_Planning] RFQ: /home/user/JCE/FP/VP527224/Cost_Planning/JCE_RFQ_Cost_Planning_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Cost_Planning.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Cost Planning: 12:00 pm AEST Thu 15/10/2026
1 | VP527224 | Environment and ecology (VP527224) | C&R Consulting (Townsville) |  | TBC - phone |  | [VP527224 Environment_and_Ecology] RFQ: /home/user/JCE/FP/VP527224/Environment_and_Ecology/JCE_RFQ_Environment_and_Ecology_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Environment_and_Ecology.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Environment and Ecology: 12:00 pm AEST Thu 15/10/2026 |  | Alternative: Reef Ecologic
1 | TN-1640786 | Cost planning (quantity surveyor) (TN-1640786) | CPP Quantity Surveyors (Sydney) |  | TBC - phone |  | [TN-1640786 Cost_Planning] RFQ: /home/user/JCE/FP/TN-1640786/Cost_Planning/JCE_RFQ_Cost_Planning_Mid-Western-Contributions-Plan_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_TN-1640786_Cost_Planning.pdf | TN-1640786 Cost Planning: 12:00 pm Thu 15/10/2026 |  | cppqs.com.au; fallback only
1 | VP527224 | Geotechnical (VP527224) | Complete Geotechnical & Structural Solutions (Cairns) |  | TBC - phone | (07) 4032 6200 | [VP527224 Geotechnical] RFQ: /home/user/JCE/FP/VP527224/Geotechnical/JCE_RFQ_Geotechnical_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Geotechnical.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Geotechnical: 12:00 pm AEST Thu 15/10/2026 |  | Yellow Pages listing: verify
1 | VP527224 | Economics and engagement (VP527224) | Cummings Economics (Cairns) |  | TBC - phone | 07 4031 2888; 0418 871 011 | [VP527224 Economics_and_Engagement] RFQ: /home/user/JCE/FP/VP527224/Economics_and_Engagement/JCE_RFQ_Economics_and_Engagement_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Economics_and_Engagement.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Economics and Engagement: 12:00 pm AEST Thu 15/10/2026
1 | VP527224 | Geotechnical (VP527224) | Douglas Partners (Cairns office) |  | TBC - phone |  | [VP527224 Geotechnical] RFQ: /home/user/JCE/FP/VP527224/Geotechnical/JCE_RFQ_Geotechnical_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Geotechnical.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Geotechnical: 12:00 pm AEST Thu 15/10/2026 |  | Cairns office to confirm
1 | VP527224 | Town planning (VP527224) | Flanagan Consulting Group (Cairns) | Cairns office | cairns@flanaganconsulting.com.au | +61 7 4031 3199 | [VP527224 Town_Planning] RFQ: /home/user/JCE/FP/VP527224/Town_Planning/JCE_RFQ_Town_Planning_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Town_Planning.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Town Planning: 12:00 pm AEST Thu 15/10/2026
1 | TN-1640786 | Cost planning (quantity surveyor) (TN-1640786) | G J Seib Pty Ltd (Orange) |  | TBC - phone | (02) 6362 6860 | [TN-1640786 Cost_Planning] RFQ: /home/user/JCE/FP/TN-1640786/Cost_Planning/JCE_RFQ_Cost_Planning_Mid-Western-Contributions-Plan_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_TN-1640786_Cost_Planning.pdf | TN-1640786 Cost Planning: 12:00 pm Thu 15/10/2026 |  | Ring first (Orange based); gjseib.com.au; directory listing, check
1 | VP527224 | Town planning (VP527224) | Informed Architects (Freshwater QLD) | Damien Ingram | Damien@informedarchitects.com.au |  | [VP527224 Town_Planning] RFQ: /home/user/JCE/FP/VP527224/Town_Planning/JCE_RFQ_Town_Planning_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Town_Planning.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Town Planning: 12:00 pm AEST Thu 15/10/2026 |  | Network; quote item A3 (urban design) only
1 | TN-1640786, BUYNSW-T026-2026, VP527277, VP527819, VP527574, VP527224, VP523438, VP527469 | Associate certifying engineer (RPEQ, NER) for all pursued bids; also RFQ: civil supervision RPE Vic (VP527574) | Lotay Civil (Ballarat) | Sunny Lotay | info@lotaycivil.com.au | 0449 018 519 | Associate agreement draft: /home/user/JCE/Outreach/forms/Associate_Agreement_Sunny_Lotay_DRAFT.pdf ; Consent form: /home/user/JCE/Outreach/forms/Sunny_Consent_and_Details_Form.pdf [VP527574 Civil_Supervision_RPEV] RFQ: /home/user/JCE/FP/VP527574/Civil_Supervision_RPEV/JCE_RFQ_Civil-Supervision-RPEV_Newstead-Levee-Design_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527574_Civil_Supervision_RPEV.pdf + Attachment_1-Project_Brief_and_General_Specification.pdf (Dropbox discipline folder) | Consent, RPEQ/NER numbers, CV, insurance by Thu 15/10/2026 VP527574 civil supervision quote: 12:00 pm Fri 16/10/2026 |  | Email not confirmed online; confirm by phone. Allowances in FPs at $200/hr (VP527277 at $220/hr) [TBC]
1 | VP527224 | Economics and engagement (VP527224) | Lucid Economics (Brisbane) |  | TBC - phone |  | [VP527224 Economics_and_Engagement] RFQ: /home/user/JCE/FP/VP527224/Economics_and_Engagement/JCE_RFQ_Economics_and_Engagement_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Economics_and_Engagement.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Economics and Engagement: 12:00 pm AEST Thu 15/10/2026 |  | Fallback
1 | VP527224 | Environment and ecology (VP527224) | NRA Environmental Consultants (Cairns) |  | TBC - phone |  | [VP527224 Environment_and_Ecology] RFQ: /home/user/JCE/FP/VP527224/Environment_and_Ecology/JCE_RFQ_Environment_and_Ecology_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Environment_and_Ecology.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Environment and Ecology: 12:00 pm AEST Thu 15/10/2026
1 | TN-1640786 | Town planning (contributions planning) (TN-1640786) | Navigate Planning | Mark Hitchenson | mark@navigateplanning.com.au |  | [TN-1640786 Town_Planning] RFQ: /home/user/JCE/FP/TN-1640786/Town_Planning/JCE_RFQ_Town_Planning_Mid-Western-Contributions-Plan_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_TN-1640786_Town_Planning.pdf | TN-1640786 Town Planning: 12:00 pm Thu 15/10/2026 |  | Pick 1; check Navigate independence (acts for applicants in Mid-Western LGA)
1 | VP527224 | Town planning (VP527224) | RPS (Cairns office) |  | TBC - phone |  | [VP527224 Town_Planning] RFQ: /home/user/JCE/FP/VP527224/Town_Planning/JCE_RFQ_Town_Planning_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Town_Planning.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Town Planning: 12:00 pm AEST Thu 15/10/2026 |  | Alternative: Urban Sync
1 | VP527224 | Cost planning (VP527224) | Rider Levett Bucknall (Cairns) | Nick Duncan | nick.duncan@au.rlb.com |  | [VP527224 Cost_Planning] RFQ: /home/user/JCE/FP/VP527224/Cost_Planning/JCE_RFQ_Cost_Planning_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Cost_Planning.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Cost Planning: 12:00 pm AEST Thu 15/10/2026 |  | Address from a job advert: confirm right person
1 | VP527224 | Geotechnical (VP527224) | Tetra Tech Coffey (Cairns office) |  | TBC - phone |  | [VP527224 Geotechnical] RFQ: /home/user/JCE/FP/VP527224/Geotechnical/JCE_RFQ_Geotechnical_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Geotechnical.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Geotechnical: 12:00 pm AEST Thu 15/10/2026
1 | VP527224 | Environment and ecology (VP527224) | TropWATER, James Cook University (Cairns) |  | TBC - phone |  | [VP527224 Environment_and_Ecology] RFQ: /home/user/JCE/FP/VP527224/Environment_and_Ecology/JCE_RFQ_Environment_and_Ecology_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Environment_and_Ecology.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Environment and Ecology: 12:00 pm AEST Thu 15/10/2026 |  | Confirm it takes commercial sub-consultancy work
1 | VP527224 | Marine and coastal engineering (VP527224) | Venant Solutions (QLD) | Richard Gale | richard.gale@venantsolutions.com.au |  | [VP527224 Marine_and_Coastal_Engineering] RFQ: /home/user/JCE/FP/VP527224/Marine_and_Coastal_Engineering/JCE_RFQ_Marine_and_Coastal_Engineering_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Marine_and_Coastal_Engineering.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Marine and Coastal Engineering: 12:00 pm AEST Thu 15/10/2026 |  | Reply to Richard's 27/07 Cameron Place proposal first (owed)
1 | VP527224 | Cost planning (VP527224) | WT Partnership (Brisbane) |  | TBC - phone |  | [VP527224 Cost_Planning] RFQ: /home/user/JCE/FP/VP527224/Cost_Planning/JCE_RFQ_Cost_Planning_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Cost_Planning.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Cost Planning: 12:00 pm AEST Thu 15/10/2026
1 | TN-1640786 | Cost planning (quantity surveyor) (TN-1640786) | Walton Smith Consultants |  | TBC - phone |  | [TN-1640786 Cost_Planning] RFQ: /home/user/JCE/FP/TN-1640786/Cost_Planning/JCE_RFQ_Cost_Planning_Mid-Western-Contributions-Plan_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_TN-1640786_Cost_Planning.pdf | TN-1640786 Cost Planning: 12:00 pm Thu 15/10/2026 |  | wsconsult.com.au; no phone found
1 | VP527224 | Marine and coastal engineering (VP527224) | Water Technology (Brisbane) |  | TBC - phone |  | [VP527224 Marine_and_Coastal_Engineering] RFQ: /home/user/JCE/FP/VP527224/Marine_and_Coastal_Engineering/JCE_RFQ_Marine_and_Coastal_Engineering_VP527224_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527224_Marine_and_Coastal_Engineering.pdf + Council_Scope_2026-092_PART5.pdf (Dropbox discipline folder) | VP527224 Marine and Coastal Engineering: 12:00 pm AEST Thu 15/10/2026 |  | Alternative: International Coastal Management
1 | TN-1640786, BUYNSW-T026-2026, VP527277, VP527819, VP527574, VP527224, VP523438, VP527469 | Insurance broker: PL $20M, workers comp, motor, drone liability | Webber (insurance broker) | [Broker TBC] | TBC - phone |  | Email in EMAIL_TEMPLATES.md (no attachment; optionally the insurance clauses from each RFQ) | Quote/bind PL $20M before first lodgement: by Thu 15/10/2026 (TN-1640786 lodge 16/10, VP527224 21/10) |  | PL $20M quote requested 12/10 per checklists: chase and bind
1 | BUYNSW-T026-2026, VP523438, VP527224, VP527574 | Referee: Katherine Aquatics, Katherine NT (about $10M D&C). Need client contact name, position, phone, email, dates | Katherine Aquatics (Sitzler / Katherine Town Council) | [Contact TBC] | TBC - phone |  | Referee_Consent_Form: /home/user/JCE/Outreach/forms/Referee_Consent_Form.pdf (email template in EMAIL_TEMPLATES.md) | Reply by Fri 16/10/2026 (earliest lodgement: TN-1640786 lodge by 16/10) |  | Jayden to identify the right Sitzler or Council contact
1 | VP527277, VP527819, VP527574, VP527224, VP523438, VP527469 | Referee: Farm drainage drone survey. Ask consent, phone, email, location, year, area | Private client (farm drainage drone survey) | Craig Sullivan | TBC - phone |  | Referee_Consent_Form: /home/user/JCE/Outreach/forms/Referee_Consent_Form.pdf (email template in EMAIL_TEMPLATES.md) | Reply by Fri 16/10/2026 (earliest lodgement: TN-1640786 lodge by 16/10) |  | FPs print 'Referee details available on request'
1 | BUYNSW-T026-2026, VP527469, VP527574 | Referee: WSI Business Precinct Stage One (JCE sub-consultant). Need referee contact and project value | Underscore Projects (WSI Airport Business Precinct, client AT&L) | [Contact TBC] | TBC - phone |  | Referee_Consent_Form: /home/user/JCE/Outreach/forms/Referee_Consent_Form.pdf (email template in EMAIL_TEMPLATES.md) | Reply by Fri 16/10/2026 (earliest lodgement: TN-1640786 lodge by 16/10) |  | Permission to list WSI work (VP527574 checklist item 8)
1 | VP527574 | Supplementary survey and survey day rate (VP527574) | Adrian Cummins & Associates (East Bendigo) |  | TBC - phone | (03) 5442 5133 | [VP527574 Survey] RFQ: /home/user/JCE/FP/VP527574/Survey/JCE_RFQ_Survey_Newstead-Levee-Design_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527574_Survey.pdf + Attachment_1-Project_Brief_and_General_Specification.pdf (Dropbox discipline folder) | VP527574 Survey: 12:00 pm Fri 16/10/2026 (AEDT) |  | Licensed surveyor, local
1 | VP527574 | Supplementary survey and survey day rate (VP527574) | BCE Spatial Pty Ltd (Travancore VIC) | Gerald Donn | gerald@bcespatial.com.au |  | [VP527574 Survey] RFQ: /home/user/JCE/FP/VP527574/Survey/JCE_RFQ_Survey_Newstead-Levee-Design_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527574_Survey.pdf + Attachment_1-Project_Brief_and_General_Specification.pdf (Dropbox discipline folder) | VP527574 Survey: 12:00 pm Fri 16/10/2026 (AEDT) |  | Not local
1 | BUYNSW-T026-2026 | Lead Architect teaming: JCE as civil sub-consultant (BUYNSW-T026-2026) | Brewster Hjorth Architects |  | bha@brewsterhjorth.com.au (check: now part of Fuse Architects) |  | [BUYNSW-T026-2026] Teaming brief Rev D: /home/user/JCE/FP/BUYNSW-T026-2026/Architect-Teaming/JCE_Teaming_Architect-Teaming_Leppington_Final_Brewster-Hjorth.pdf + RFT-T026-2026_-Volume-4-_-Consultants-Brief.pdf, RFT-T026-2026-Addendum-_01.doc, T026-2026-Addendum-2.pdf (Dropbox 03_Subconsultants/Lead_Architect). No Quote Return Form (JCE is the sub-consultant). Do not send the _RevC files. | BUYNSW-T026-2026: confirm teaming by Fri 16/10/2026 |  | Confirm address / approach Fuse instead; Email text: FP/BUYNSW-T026-2026/Architect-Teaming/Emails.txt
1 | BUYNSW-T026-2026 | Lead Architect teaming: JCE as civil sub-consultant (BUYNSW-T026-2026) | Carter Williamson Architects |  | studio@carterwilliamson.com |  | [BUYNSW-T026-2026] Teaming brief Rev D: /home/user/JCE/FP/BUYNSW-T026-2026/Architect-Teaming/JCE_Teaming_Architect-Teaming_Leppington_Final_Carter-Williamson.pdf + RFT-T026-2026_-Volume-4-_-Consultants-Brief.pdf, RFT-T026-2026-Addendum-_01.doc, T026-2026-Addendum-2.pdf (Dropbox 03_Subconsultants/Lead_Architect). No Quote Return Form (JCE is the sub-consultant). Do not send the _RevC files. | BUYNSW-T026-2026: confirm teaming by Fri 16/10/2026 |  | Email text: FP/BUYNSW-T026-2026/Architect-Teaming/Emails.txt
1 | VP527574, VP527469 | Geotechnical investigation and design advice (PS-A) (VP527574) Geotechnical (Riverina CQA partner) (VP527469) | Civiltest Pty Ltd |  | TBC - phone |  | [VP527574 Geotechnical] RFQ: /home/user/JCE/FP/VP527574/Geotechnical/JCE_RFQ_Geotechnical_Newstead-Levee-Design_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527574_Geotechnical.pdf + Attachment_1-Project_Brief_and_General_Specification.pdf (Dropbox discipline folder) [VP527469 Geotechnical] RFQ: /home/user/JCE/FP/VP527469/Geotechnical/JCE_RFQ_VP527469_Geotechnical_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527469_Geotechnical.pdf + tender extracts listed in the discipline Emails.txt (Attachments A, B, E and F/C/G or Part D) | VP527574 Geotechnical: 12:00 pm Fri 16/10/2026 (AEDT) VP527469 Geotechnical: 12:00 pm Fri 23/10/2026 |  | civiltest.com.au; Mitcham, Mildura, Wodonga offices; Wodonga office
1 | BUYNSW-T026-2026 | Lead Architect teaming: JCE as civil sub-consultant (BUYNSW-T026-2026) | DJAS Architecture | Adam Litherland | ALitherland@djas.com.au |  | [BUYNSW-T026-2026] Teaming brief Rev D: /home/user/JCE/FP/BUYNSW-T026-2026/Architect-Teaming/JCE_Teaming_Architect-Teaming_Leppington_Final_DJAS-Architecture.pdf + RFT-T026-2026_-Volume-4-_-Consultants-Brief.pdf, RFT-T026-2026-Addendum-_01.doc, T026-2026-Addendum-2.pdf (Dropbox 03_Subconsultants/Lead_Architect). No Quote Return Form (JCE is the sub-consultant). Do not send the _RevC files. | BUYNSW-T026-2026: confirm teaming by Fri 16/10/2026 |  | Email text: FP/BUYNSW-T026-2026/Architect-Teaming/Emails.txt
1 | BUYNSW-T026-2026 | Lead Architect teaming: JCE as civil sub-consultant (BUYNSW-T026-2026) | DRA Architects | Peter Way | pway@draarchitects.com.au |  | [BUYNSW-T026-2026] Teaming brief Rev D: /home/user/JCE/FP/BUYNSW-T026-2026/Architect-Teaming/JCE_Teaming_Architect-Teaming_Leppington_Final_DRA-Architects.pdf + RFT-T026-2026_-Volume-4-_-Consultants-Brief.pdf, RFT-T026-2026-Addendum-_01.doc, T026-2026-Addendum-2.pdf (Dropbox 03_Subconsultants/Lead_Architect). No Quote Return Form (JCE is the sub-consultant). Do not send the _RevC files. | BUYNSW-T026-2026: confirm teaming by Fri 16/10/2026 |  | Email text: FP/BUYNSW-T026-2026/Architect-Teaming/Emails.txt
1 | VP527574 | Geotechnical investigation and design advice (PS-A) (VP527574) | Geotechnical Testing Services (Sandhurst Geotech), Bendigo | Braam Haasbroek (BDM) | info@geotestsouthern.com.au | 03 5441 4881; 0468 309 929 (Braam) | [VP527574 Geotechnical] RFQ: /home/user/JCE/FP/VP527574/Geotechnical/JCE_RFQ_Geotechnical_Newstead-Levee-Design_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527574_Geotechnical.pdf + Attachment_1-Project_Brief_and_General_Specification.pdf (Dropbox discipline folder) | VP527574 Geotechnical: 12:00 pm Fri 16/10/2026 (AEDT) |  | Local (Bendigo)
1 | VP527574 | Floodplain modelling and hydraulic impact assessment (VP527574) | HARC (Blackburn VIC) |  | TBC - phone | 03 9908 2160 | [VP527574 Floodplain_Modelling] RFQ: /home/user/JCE/FP/VP527574/Floodplain_Modelling/JCE_RFQ_Floodplain-Modelling_Newstead-Levee-Design_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527574_Floodplain_Modelling.pdf + Attachment_1-Project_Brief_and_General_Specification.pdf (Dropbox discipline folder) | VP527574 Floodplain Modelling: 12:00 pm Fri 16/10/2026 (AEDT) |  | harc.com.au contact page
1 | VP527574 | Geotechnical investigation and design advice (PS-A) (VP527574) | Provincial Geotechnical |  | TBC - phone |  | [VP527574 Geotechnical] RFQ: /home/user/JCE/FP/VP527574/Geotechnical/JCE_RFQ_Geotechnical_Newstead-Levee-Design_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527574_Geotechnical.pdf + Attachment_1-Project_Brief_and_General_Specification.pdf (Dropbox discipline folder) | VP527574 Geotechnical: 12:00 pm Fri 16/10/2026 (AEDT) |  | 11/10 draft had admin@pgvic.com.au (not confirmed)
1 | VP527574 | Civil design supervision and approval (RPE Vic, Civil) (VP527574) Supplementary survey and survey day rate (VP527574) | Spiire (Bendigo office) |  | TBC - phone | 03 5448 2500 | [VP527574 Civil_Supervision_RPEV] RFQ: /home/user/JCE/FP/VP527574/Civil_Supervision_RPEV/JCE_RFQ_Civil-Supervision-RPEV_Newstead-Levee-Design_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527574_Civil_Supervision_RPEV.pdf + Attachment_1-Project_Brief_and_General_Specification.pdf (Dropbox discipline folder) [VP527574 Survey] RFQ: /home/user/JCE/FP/VP527574/Survey/JCE_RFQ_Survey_Newstead-Levee-Design_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527574_Survey.pdf + Attachment_1-Project_Brief_and_General_Specification.pdf (Dropbox discipline folder) | VP527574 Civil Supervision RPEV: 12:00 pm Fri 16/10/2026 (AEDT) VP527574 Survey: 12:00 pm Fri 16/10/2026 (AEDT) |  | 16 Bridge St Bendigo (2017 drawing); local content
1 | VP527574 | Floodplain modelling and hydraulic impact assessment (VP527574) Civil design supervision and approval (RPE Vic, Civil) (VP527574) | Venant Solutions | Michael South (cc Atoosa Towzihian) | michael.south@venantsolutions.com.au; cc atoosa.towzihian@venantsolutions.com.au |  | [VP527574 Floodplain_Modelling] RFQ: /home/user/JCE/FP/VP527574/Floodplain_Modelling/JCE_RFQ_Floodplain-Modelling_Newstead-Levee-Design_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527574_Floodplain_Modelling.pdf + Attachment_1-Project_Brief_and_General_Specification.pdf (Dropbox discipline folder) [VP527574 Civil_Supervision_RPEV] RFQ: /home/user/JCE/FP/VP527574/Civil_Supervision_RPEV/JCE_RFQ_Civil-Supervision-RPEV_Newstead-Levee-Design_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527574_Civil_Supervision_RPEV.pdf + Attachment_1-Project_Brief_and_General_Specification.pdf (Dropbox discipline folder) | VP527574 Floodplain Modelling: 12:00 pm Fri 16/10/2026 (AEDT) VP527574 Civil Supervision RPEV: 12:00 pm Fri 16/10/2026 (AEDT) |  | JCE partner; also civil supervision fallback (only if RPE area covers civil)
1 | BUYNSW-T026-2026 | Lead Architect teaming: JCE as civil sub-consultant (BUYNSW-T026-2026) | Vibe Architects | Jason McCarthy | jason@vibearchitects.com.au |  | [BUYNSW-T026-2026] Teaming brief Rev D: /home/user/JCE/FP/BUYNSW-T026-2026/Architect-Teaming/JCE_Teaming_Architect-Teaming_Leppington_Final_Vibe-Architects.pdf + RFT-T026-2026_-Volume-4-_-Consultants-Brief.pdf, RFT-T026-2026-Addendum-_01.doc, T026-2026-Addendum-2.pdf (Dropbox 03_Subconsultants/Lead_Architect). No Quote Return Form (JCE is the sub-consultant). Do not send the _RevC files. | BUYNSW-T026-2026: confirm teaming by Fri 16/10/2026 |  | Referred work to JCE twice; Email text: FP/BUYNSW-T026-2026/Architect-Teaming/Emails.txt
2 | VP528349 | Aurukun WMF buyer: AI-use permission question (clause 2.8(b)) | QLD DLGWV procurement (buyer, VP528349 Aurukun WMF) | Procurement | procurement@dlgwv.qld.gov.au |  | Question text in EMAIL_TEMPLATES.md (no attachment) | Questions close Mon 19/10/2026 |  | Not a pursued bid yet (draft ready, blocked on clause 2.8(b)). Exact clause wording not in local files: check before sending
2 | VP527277, VP527819 | Valuer: review and sign-off of transport and bridge asset valuations (VP527277) Valuation partner (comprehensive revaluation) (VP527819) | APV Valuers & Asset Management |  | TBC - phone | (08) 8311 3949 | [VP527277 Valuation] RFQ: /home/user/JCE/FP/VP527277/Valuation/JCE_RFQ_Valuation_MRC-Asset-Condition_Final_APV.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527277_Valuation.pdf + MRC-2645_Project_Brief.pdf and MRC-2645_asset_data_schema-data_template_August_2026.xlsx (Dropbox 03_Subconsultants/<discipline>) [VP527819 Valuation] RFQ: /home/user/JCE/FP/VP527819/Valuation/per_firm/JCE_RFQ_Valuation_IWC-Transport-Audit_Final_APV.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527819_Valuation.pdf + Council docs from Dropbox 00_Tender_Docs: Scope_Spec Final.pdf, Transport Audit - Scope table.xlsx, IWC Consultancy Agreement DRAFT.pdf | VP527277 Valuation: 12:00 pm Wed 28/10/2026 VP527819 Valuation: 12:00 pm Wed 21/10/2026 |  | apv.net; directory listing, confirm
2 | VP527277, VP527819 | Valuer: review and sign-off of transport and bridge asset valuations (VP527277) Valuation partner (comprehensive revaluation) (VP527819) | Australis Asset Advisory Group |  | TBC - phone |  | [VP527277 Valuation] RFQ: /home/user/JCE/FP/VP527277/Valuation/JCE_RFQ_Valuation_MRC-Asset-Condition_Final_Australis.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527277_Valuation.pdf + MRC-2645_Project_Brief.pdf and MRC-2645_asset_data_schema-data_template_August_2026.xlsx (Dropbox 03_Subconsultants/<discipline>) [VP527819 Valuation] RFQ: /home/user/JCE/FP/VP527819/Valuation/per_firm/JCE_RFQ_Valuation_IWC-Transport-Audit_Final_Australis.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527819_Valuation.pdf + Council docs from Dropbox 00_Tender_Docs: Scope_Spec Final.pdf, Transport Audit - Scope table.xlsx, IWC Consultancy Agreement DRAFT.pdf | VP527277 Valuation: 12:00 pm Wed 28/10/2026 VP527819 Valuation: 12:00 pm Wed 21/10/2026 |  | WALGA supplier listing
2 | VP527277, VP527819 | Road network imaging and condition rating (VP527277) Field data capture (inventory and condition audit) (VP527819) | Infrastructure Management Group (IMG) |  | TBC - phone |  | [VP527277 Road_Imaging_Condition] RFQ: /home/user/JCE/FP/VP527277/Road_Imaging_Condition/JCE_RFQ_Road_Imaging_Condition_MRC-Asset-Condition_Final_RevC_IMG.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527277_Road_Imaging_Condition.pdf + MRC-2645_Project_Brief.pdf and MRC-2645_asset_data_schema-data_template_August_2026.xlsx (Dropbox 03_Subconsultants/<discipline>) [VP527819 Condition_Data_Collection] RFQ: /home/user/JCE/FP/VP527819/Condition_Data_Collection/per_firm/JCE_RFQ_Condition_Data_Collection_IWC-Transport-Audit_Final_RevD_IMG.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527819_Condition_Data_Collection.pdf + Council docs from Dropbox 00_Tender_Docs: Scope_Spec Final.pdf, Transport Audit - Scope table.xlsx, IWC Consultancy Agreement DRAFT.pdf | VP527277 Road Imaging Condition: 12:00 pm Wed 28/10/2026 VP527819 Condition Data Collection: 12:00 pm Wed 21/10/2026 |  | May tender MRC-2645 directly: ask. Same firm as VP527819 data capture; Did Council's 2021 inspection; likely to bid direct
2 | VP527277, VP527819 | Valuer: review and sign-off of transport and bridge asset valuations (VP527277) Valuation partner (comprehensive revaluation) (VP527819) | Jeff Roorda & Associates (JRA) |  | TBC - phone |  | [VP527277 Valuation] RFQ: /home/user/JCE/FP/VP527277/Valuation/JCE_RFQ_Valuation_MRC-Asset-Condition_Final_JRA.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527277_Valuation.pdf + MRC-2645_Project_Brief.pdf and MRC-2645_asset_data_schema-data_template_August_2026.xlsx (Dropbox 03_Subconsultants/<discipline>) [VP527819 Valuation] RFQ: /home/user/JCE/FP/VP527819/Valuation/per_firm/JCE_RFQ_Valuation_IWC-Transport-Audit_Final_JRA.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527819_Valuation.pdf + Council docs from Dropbox 00_Tender_Docs: Scope_Spec Final.pdf, Transport Audit - Scope table.xlsx, IWC Consultancy Agreement DRAFT.pdf | VP527277 Valuation: 12:00 pm Wed 28/10/2026 VP527819 Valuation: 12:00 pm Wed 21/10/2026 |  | No website or contact found: confirm still trading
2 | VP527819 | Field data capture (inventory and condition audit) (VP527819) | Moloney Asset Management Systems | Peter Moloney | peter@moloneys.com.au |  | [VP527819 Condition_Data_Collection] RFQ: /home/user/JCE/FP/VP527819/Condition_Data_Collection/per_firm/JCE_RFQ_Condition_Data_Collection_IWC-Transport-Audit_Final_RevD_Moloney.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527819_Condition_Data_Collection.pdf + Council docs from Dropbox 00_Tender_Docs: Scope_Spec Final.pdf, Transport Audit - Scope table.xlsx, IWC Consultancy Agreement DRAFT.pdf | VP527819 Condition Data Collection: 12:00 pm Wed 21/10/2026 |  | Address from 2015 reports: confirm current
2 | VP527819 | Field data capture (inventory and condition audit) (VP527819) | Pavement Management Services Pty Ltd (Seven Hills) | Regional Manager | TBC - phone | 02 9674 9488 | [VP527819 Condition_Data_Collection] RFQ: /home/user/JCE/FP/VP527819/Condition_Data_Collection/per_firm/JCE_RFQ_Condition_Data_Collection_IWC-Transport-Audit_Final_RevD_PMS.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527819_Condition_Data_Collection.pdf + Council docs from Dropbox 00_Tender_Docs: Scope_Spec Final.pdf, Transport Audit - Scope table.xlsx, IWC Consultancy Agreement DRAFT.pdf | VP527819 Condition Data Collection: 12:00 pm Wed 21/10/2026 |  | Confirm current entity and footpath capability
2 | VP527469 | Geotechnical (Riverina CQA partner) (VP527469) | AC Testing Services (fallback, New England) | Adam | adam@actestingservices.com.au |  | [VP527469 Geotechnical] RFQ: /home/user/JCE/FP/VP527469/Geotechnical/JCE_RFQ_VP527469_Geotechnical_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527469_Geotechnical.pdf + tender extracts listed in the discipline Emails.txt (Attachments A, B, E and F/C/G or Part D) | VP527469 Geotechnical: 12:00 pm Fri 23/10/2026 |  | Network fallback named in README; send only if Riverina firms decline
2 | VP523438 | Arborist and Vegetation (VP523438) | Adelaide ARB Consultants |  | info@adelaidearb.com.au |  | [VP523438 Arborist_and_Vegetation] RFQ: /home/user/JCE/FP/VP523438/Arborist_and_Vegetation/JCE_RFQ_Arborist_and_Vegetation_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Arborist_and_Vegetation.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Arborist and Vegetation: 12:00 pm ACDT Fri 23/10/2026
2 | VP523438 | Geotechnical (VP523438) | Aeolian Geotechnical (Mount Barker) | Chris Eastham | c.eastham@aeoliangeo.com.au | 0484 119 360 | [VP523438 Geotechnical] RFQ: /home/user/JCE/FP/VP523438/Geotechnical/JCE_RFQ_Geotechnical_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Geotechnical.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Geotechnical: 12:00 pm ACDT Fri 23/10/2026 |  | Ask if they do interpretive report and pavement design
2 | VP527469 | Geotechnical (Riverina CQA partner) (VP527469) | Aitken Rowe Testing Laboratories (East Wagga Wagga) |  | TBC - phone | (02) 6939 5555 | [VP527469 Geotechnical] RFQ: /home/user/JCE/FP/VP527469/Geotechnical/JCE_RFQ_VP527469_Geotechnical_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527469_Geotechnical.pdf + tender extracts listed in the discipline Emails.txt (Attachments A, B, E and F/C/G or Part D) | VP527469 Geotechnical: 12:00 pm Fri 23/10/2026 |  | aitkenrowe.com.au
2 | VP523438 | Survey (VP523438) | Alexander Symonds |  | adelaide@alexander.com.au | (08) 8130 1666 | [VP523438 Survey] RFQ: /home/user/JCE/FP/VP523438/Survey/JCE_RFQ_Survey_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Survey.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Survey: 12:00 pm ACDT Fri 23/10/2026
2 | VP527469 | Check survey (Planes 1 to 3) (VP527469) | Amey (Wagga Wagga office) |  | waggawagga@amey.com.au | (02) 6921 3312 | [VP527469 Survey] RFQ: /home/user/JCE/FP/VP527469/Survey/JCE_RFQ_VP527469_Survey_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527469_Survey.pdf + tender extracts listed in the discipline Emails.txt (Attachments A, B, E and F/C/G or Part D) | VP527469 Survey: 12:00 pm Fri 23/10/2026 |  | Check for any role with Head Contractor or designer
2 | VP523438 | Arborist and Vegetation (VP523438) | Arborman Tree Solutions | Marcus Lodge | arborman@arborman.com.au | (08) 8240 5555 | [VP523438 Arborist_and_Vegetation] RFQ: /home/user/JCE/FP/VP523438/Arborist_and_Vegetation/JCE_RFQ_Arborist_and_Vegetation_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Arborist_and_Vegetation.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Arborist and Vegetation: 12:00 pm ACDT Fri 23/10/2026
2 | VP523438 | Traffic and Road Safety Audit (VP523438) | BE Engineering Solutions |  | info@be-engsolutions.com.au |  | [VP523438 Traffic_and_Road_Safety_Audit] RFQ: /home/user/JCE/FP/VP523438/Traffic_and_Road_Safety_Audit/JCE_RFQ_Traffic_and_Road_Safety_Audit_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Traffic_and_Road_Safety_Audit.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Traffic and Road Safety Audit: 12:00 pm ACDT Fri 23/10/2026
2 | VP523438 | Street Lighting (VP523438) | BESTEC |  | TBC - phone |  | [VP523438 Street_Lighting] RFQ: /home/user/JCE/FP/VP523438/Street_Lighting/JCE_RFQ_Street_Lighting_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Street_Lighting.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Street Lighting: 12:00 pm ACDT Fri 23/10/2026 |  | Office address to confirm
2 | VP523438 | Traffic and Road Safety Audit (VP523438) | CIRQA |  | TBC - phone |  | [VP523438 Traffic_and_Road_Safety_Audit] RFQ: /home/user/JCE/FP/VP523438/Traffic_and_Road_Safety_Audit/JCE_RFQ_Traffic_and_Road_Safety_Audit_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Traffic_and_Road_Safety_Audit.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Traffic and Road Safety Audit: 12:00 pm ACDT Fri 23/10/2026
2 | VP523438 | Street Lighting (VP523438) | Clarence Consultants (Coffs Harbour) | Ken Heard | Ken@clarenceconsultants.com.au |  | [VP523438 Street_Lighting] RFQ: /home/user/JCE/FP/VP523438/Street_Lighting/JCE_RFQ_Street_Lighting_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Street_Lighting.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Street Lighting: 12:00 pm ACDT Fri 23/10/2026 |  | Network; ask about SAPN experience
2 | VP523438 | Geotechnical (VP523438) | Douglas Partners (Adelaide office) |  | TBC - phone |  | [VP523438 Geotechnical] RFQ: /home/user/JCE/FP/VP523438/Geotechnical/JCE_RFQ_Geotechnical_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Geotechnical.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Geotechnical: 12:00 pm ACDT Fri 23/10/2026
2 | VP523438 | Arborist and Vegetation (VP523438) | ENSPEC | Craig Hallam | craig.hallam@enspec.com | +61 417 027 152 | [VP523438 Arborist_and_Vegetation] RFQ: /home/user/JCE/FP/VP523438/Arborist_and_Vegetation/JCE_RFQ_Arborist_and_Vegetation_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Arborist_and_Vegetation.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Arborist and Vegetation: 12:00 pm ACDT Fri 23/10/2026
2 | VP527469 | Geosynthetics (NATA IQA testing, leak location surveys) (VP527469) | ExcelPlas Pty Ltd (Highett VIC) |  | TBC - phone | (03) 9532 2207 | [VP527469 Geosynthetics] RFQ: /home/user/JCE/FP/VP527469/Geosynthetics/JCE_RFQ_VP527469_Geosynthetics_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527469_Geosynthetics.pdf + tender extracts listed in the discipline Emails.txt (Attachments A, B, E and F/C/G or Part D) | VP527469 Geosynthetics: 12:00 pm Fri 23/10/2026 |  | Confirm NATA scope covers GCL and geotextile
2 | VP527469 | Geosynthetics (NATA IQA testing, leak location surveys) (VP527469) | GeoQ (QLD) |  | TBC - phone |  | [VP527469 Geosynthetics] RFQ: /home/user/JCE/FP/VP527469/Geosynthetics/JCE_RFQ_VP527469_Geosynthetics_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527469_Geosynthetics.pdf + tender extracts listed in the discipline Emails.txt (Attachments A, B, E and F/C/G or Part D) | VP527469 Geosynthetics: 12:00 pm Fri 23/10/2026 |  | Part B leak location only; verify business
2 | VP527469 | Geotechnical (Riverina CQA partner) (VP527469) | Inland Geotechnical (East Wagga Wagga) |  | TBC - phone |  | [VP527469 Geotechnical] RFQ: /home/user/JCE/FP/VP527469/Geotechnical/JCE_RFQ_VP527469_Geotechnical_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527469_Geotechnical.pdf + tender extracts listed in the discipline Emails.txt (Attachments A, B, E and F/C/G or Part D) | VP527469 Geotechnical: 12:00 pm Fri 23/10/2026
2 | VP523438 | Street Lighting (VP523438) | Lucid Consulting Engineers (Adelaide) |  | TBC - phone | (08) 8407 9700 | [VP523438 Street_Lighting] RFQ: /home/user/JCE/FP/VP523438/Street_Lighting/JCE_RFQ_Street_Lighting_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Street_Lighting.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Street Lighting: 12:00 pm ACDT Fri 23/10/2026
2 | VP523438 | Survey (VP523438) | Mosel Surveyors |  | info@mosel.com.au | (08) 8821 3544 | [VP523438 Survey] RFQ: /home/user/JCE/FP/VP523438/Survey/JCE_RFQ_Survey_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Survey.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Survey: 12:00 pm ACDT Fri 23/10/2026
2 | VP527469 | Check survey (Planes 1 to 3) (VP527469) | Rivland Surveyors (Wagga Wagga) | Chris | chris@rivland.com.au | 02 6971 8811 | [VP527469 Survey] RFQ: /home/user/JCE/FP/VP527469/Survey/JCE_RFQ_VP527469_Survey_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527469_Survey.pdf + tender extracts listed in the discipline Emails.txt (Attachments A, B, E and F/C/G or Part D) | VP527469 Survey: 12:00 pm Fri 23/10/2026 |  | Email from 2019-20 plan: confirm
2 | VP523438 | Traffic and Road Safety Audit (VP523438) | SALT (Adelaide) |  | adelaide@salt3.com.au |  | [VP523438 Traffic_and_Road_Safety_Audit] RFQ: /home/user/JCE/FP/VP523438/Traffic_and_Road_Safety_Audit/JCE_RFQ_Traffic_and_Road_Safety_Audit_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Traffic_and_Road_Safety_Audit.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Traffic and Road Safety Audit: 12:00 pm ACDT Fri 23/10/2026
2 | VP523438 | Survey (VP523438) | Steed Surveyors (Mount Barker) |  | TBC - phone | (08) 8391 3000 | [VP523438 Survey] RFQ: /home/user/JCE/FP/VP523438/Survey/JCE_RFQ_Survey_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Survey.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Survey: 12:00 pm ACDT Fri 23/10/2026 |  | Local
2 | VP527469 | Geosynthetics (NATA IQA testing, leak location surveys) (VP527469) | TRI Australasia Pty Ltd | Benjamin Hart | TBC - phone | 0457 442 721 | [VP527469 Geosynthetics] RFQ: /home/user/JCE/FP/VP527469/Geosynthetics/JCE_RFQ_VP527469_Geosynthetics_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527469_Geosynthetics.pdf + tender extracts listed in the discipline Emails.txt (Attachments A, B, E and F/C/G or Part D) | VP527469 Geosynthetics: 12:00 pm Fri 23/10/2026 |  | Ask if they nominate a leak location partner
2 | VP527469 | Check survey (Planes 1 to 3) (VP527469) | Wagga Surveyors Pty Ltd |  | admin@waggasurveyors.com.au | 02 6931 7099 | [VP527469 Survey] RFQ: /home/user/JCE/FP/VP527469/Survey/JCE_RFQ_VP527469_Survey_Final.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527469_Survey.pdf + tender extracts listed in the discipline Emails.txt (Attachments A, B, E and F/C/G or Part D) | VP527469 Survey: 12:00 pm Fri 23/10/2026 |  | Email from 2022 plan: confirm
2 | VP523438 | Geotechnical (VP523438) | Wallbridge Gilbert Aztec (WGA) | Brenton Harris | TBC - phone |  | [VP523438 Geotechnical] RFQ: /home/user/JCE/FP/VP523438/Geotechnical/JCE_RFQ_Geotechnical_Hawthorn-Road-Concept-Design_FINAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP523438_Geotechnical.pdf + 2026.013-Concept_Design_for_Hawthorn_Road-Project_Brief.pdf | VP523438 Geotechnical: 12:00 pm ACDT Fri 23/10/2026 |  | May tender as lead designer: ask first
3 | VP527277 | Level 2 bridge, major culvert and footbridge inspections (VP527277) | BK-ECS (Grafton) | Simon Bruce | simon.b@bk-ecs.com.au |  | [VP527277 Bridge_Inspection] RFQ: /home/user/JCE/FP/VP527277/Bridge_Inspection/JCE_RFQ_Bridge_Inspection_MRC-Asset-Condition_Final_BK-ECS.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527277_Bridge_Inspection.pdf + MRC-2645_Project_Brief.pdf and MRC-2645_asset_data_schema-data_template_August_2026.xlsx (Dropbox 03_Subconsultants/<discipline>) | VP527277 Bridge Inspection: 12:00 pm Wed 28/10/2026 |  | Network; bridge experience not confirmed
3 | VP527277 | Level 2 bridge, major culvert and footbridge inspections (VP527277) | Lancini Consulting | Ben Lancini | ben.lancini@lanciniconsulting.com.au |  | [VP527277 Bridge_Inspection] RFQ: /home/user/JCE/FP/VP527277/Bridge_Inspection/JCE_RFQ_Bridge_Inspection_MRC-Asset-Condition_Final_Lancini.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527277_Bridge_Inspection.pdf + MRC-2645_Project_Brief.pdf and MRC-2645_asset_data_schema-data_template_August_2026.xlsx (Dropbox 03_Subconsultants/<discipline>) | VP527277 Bridge Inspection: 12:00 pm Wed 28/10/2026 |  | Network; bridge inspection experience not confirmed: call first
3 | VP527277 | Level 2 bridge, major culvert and footbridge inspections (VP527277) | MAL Engineers | Michael Lancini | michael.lancini@malengineers.com.au |  | [VP527277 Bridge_Inspection] RFQ: /home/user/JCE/FP/VP527277/Bridge_Inspection/JCE_RFQ_Bridge_Inspection_MRC-Asset-Condition_Final_MAL.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527277_Bridge_Inspection.pdf + MRC-2645_Project_Brief.pdf and MRC-2645_asset_data_schema-data_template_August_2026.xlsx (Dropbox 03_Subconsultants/<discipline>) | VP527277 Bridge Inspection: 12:00 pm Wed 28/10/2026 |  | Network; bridge experience not confirmed
3 | VP527277 | Road network imaging and condition rating (VP527277) | NTRO (formerly ARRB) |  | TBC - phone |  | [VP527277 Road_Imaging_Condition] RFQ: /home/user/JCE/FP/VP527277/Road_Imaging_Condition/JCE_RFQ_Road_Imaging_Condition_MRC-Asset-Condition_Final_RevC_NTRO.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527277_Road_Imaging_Condition.pdf + MRC-2645_Project_Brief.pdf and MRC-2645_asset_data_schema-data_template_August_2026.xlsx (Dropbox 03_Subconsultants/<discipline>) | VP527277 Road Imaging Condition: 12:00 pm Wed 28/10/2026 |  | Confirm roadside, culvert and unsealed inventory coverage
3 | VP527277 | Road network imaging and condition rating (VP527277) | Shepherd Services |  | TBC - phone |  | [VP527277 Road_Imaging_Condition] RFQ: /home/user/JCE/FP/VP527277/Road_Imaging_Condition/JCE_RFQ_Road_Imaging_Condition_MRC-Asset-Condition_Final_RevC_Shepherd.pdf ; Quote form: /home/user/JCE/Outreach/forms/QuoteReturn_VP527277_Road_Imaging_Condition.pdf + MRC-2645_Project_Brief.pdf and MRC-2645_asset_data_schema-data_template_August_2026.xlsx (Dropbox 03_Subconsultants/<discipline>) | VP527277 Road Imaging Condition: 12:00 pm Wed 28/10/2026 |  | Services not verified: check website first

## Missing emails
Firm | Contact | Bid(s) | Discipline/role | Phone (where known) | Due | Where to find the email
Tablelands Regional Council | Darren Quilliam | TN-1640786, BUYNSW-T026-2026, VP527277, VP527819, VP527574, VP527224, VP523438, VP527469 | Referee: Ravenshoe leachate storage facility and floodway rectification (Jayden at Langtree Consulting). Ask consent, title, phone, email | Not found: use website contact page | Reply by Thu 15/10/2026 (earliest lodgement: TN-1640786 lodge by 16/10) | Get his number from Tablelands Regional Council switchboard or Jayden's Langtree records
AEC Group (Townsville) |  | VP527224 | Economics and engagement (VP527224) | Not found: use website contact page | VP527224 Economics and Engagement: 12:00 pm AEST Thu 15/10/2026
BMT (Brisbane) |  | VP527224 | Marine and coastal engineering (VP527224) | Not found: use website contact page | VP527224 Marine and Coastal Engineering: 12:00 pm AEST Thu 15/10/2026
Beacon Consulting (QLD) |  | VP527224 | Cost planning (VP527224) | Not found: use website contact page | VP527224 Cost Planning: 12:00 pm AEST Thu 15/10/2026
C&R Consulting (Townsville) |  | VP527224 | Environment and ecology (VP527224) | Not found: use website contact page | VP527224 Environment and Ecology: 12:00 pm AEST Thu 15/10/2026 | Alternative: Reef Ecologic
CPP Quantity Surveyors (Sydney) |  | TN-1640786 | Cost planning (quantity surveyor) (TN-1640786) | Not found: use website contact page | TN-1640786 Cost Planning: 12:00 pm Thu 15/10/2026 | cppqs.com.au; fallback only
Complete Geotechnical & Structural Solutions (Cairns) |  | VP527224 | Geotechnical (VP527224) | (07) 4032 6200 | VP527224 Geotechnical: 12:00 pm AEST Thu 15/10/2026 | Yellow Pages listing: verify
Cummings Economics (Cairns) |  | VP527224 | Economics and engagement (VP527224) | 07 4031 2888; 0418 871 011 | VP527224 Economics and Engagement: 12:00 pm AEST Thu 15/10/2026
Douglas Partners (Cairns office) |  | VP527224 | Geotechnical (VP527224) | Not found: use website contact page | VP527224 Geotechnical: 12:00 pm AEST Thu 15/10/2026 | Cairns office to confirm
G J Seib Pty Ltd (Orange) |  | TN-1640786 | Cost planning (quantity surveyor) (TN-1640786) | (02) 6362 6860 | TN-1640786 Cost Planning: 12:00 pm Thu 15/10/2026 | Ring first (Orange based); gjseib.com.au; directory listing, check
Lucid Economics (Brisbane) |  | VP527224 | Economics and engagement (VP527224) | Not found: use website contact page | VP527224 Economics and Engagement: 12:00 pm AEST Thu 15/10/2026 | Fallback
NRA Environmental Consultants (Cairns) |  | VP527224 | Environment and ecology (VP527224) | Not found: use website contact page | VP527224 Environment and Ecology: 12:00 pm AEST Thu 15/10/2026
RPS (Cairns office) |  | VP527224 | Town planning (VP527224) | Not found: use website contact page | VP527224 Town Planning: 12:00 pm AEST Thu 15/10/2026 | Alternative: Urban Sync
Tetra Tech Coffey (Cairns office) |  | VP527224 | Geotechnical (VP527224) | Not found: use website contact page | VP527224 Geotechnical: 12:00 pm AEST Thu 15/10/2026
TropWATER, James Cook University (Cairns) |  | VP527224 | Environment and ecology (VP527224) | Not found: use website contact page | VP527224 Environment and Ecology: 12:00 pm AEST Thu 15/10/2026 | Confirm it takes commercial sub-consultancy work
WT Partnership (Brisbane) |  | VP527224 | Cost planning (VP527224) | Not found: use website contact page | VP527224 Cost Planning: 12:00 pm AEST Thu 15/10/2026
Walton Smith Consultants |  | TN-1640786 | Cost planning (quantity surveyor) (TN-1640786) | Not found: use website contact page | TN-1640786 Cost Planning: 12:00 pm Thu 15/10/2026 | wsconsult.com.au; no phone found
Water Technology (Brisbane) |  | VP527224 | Marine and coastal engineering (VP527224) | Not found: use website contact page | VP527224 Marine and Coastal Engineering: 12:00 pm AEST Thu 15/10/2026 | Alternative: International Coastal Management
Webber (insurance broker) | [Broker TBC] | TN-1640786, BUYNSW-T026-2026, VP527277, VP527819, VP527574, VP527224, VP523438, VP527469 | Insurance broker: PL $20M, workers comp, motor, drone liability | Not found: use website contact page | Quote/bind PL $20M before first lodgement: by Thu 15/10/2026 (TN-1640786 lodge 16/10, VP527224 21/10) | PL $20M quote requested 12/10 per checklists: chase and bind
Katherine Aquatics (Sitzler / Katherine Town Council) | [Contact TBC] | BUYNSW-T026-2026, VP523438, VP527224, VP527574 | Referee: Katherine Aquatics, Katherine NT (about $10M D&C). Need client contact name, position, phone, email, dates | Not found: use website contact page | Reply by Fri 16/10/2026 (earliest lodgement: TN-1640786 lodge by 16/10) | Jayden to identify the right Sitzler or Council contact
Private client (farm drainage drone survey) | Craig Sullivan | VP527277, VP527819, VP527574, VP527224, VP523438, VP527469 | Referee: Farm drainage drone survey. Ask consent, phone, email, location, year, area | Not found: use website contact page | Reply by Fri 16/10/2026 (earliest lodgement: TN-1640786 lodge by 16/10) | FPs print 'Referee details available on request'
Underscore Projects (WSI Airport Business Precinct, client AT&L) | [Contact TBC] | BUYNSW-T026-2026, VP527469, VP527574 | Referee: WSI Business Precinct Stage One (JCE sub-consultant). Need referee contact and project value | Not found: use website contact page | Reply by Fri 16/10/2026 (earliest lodgement: TN-1640786 lodge by 16/10) | Permission to list WSI work (VP527574 checklist item 8)
Adrian Cummins & Associates (East Bendigo) |  | VP527574 | Supplementary survey and survey day rate (VP527574) | (03) 5442 5133 | VP527574 Survey: 12:00 pm Fri 16/10/2026 (AEDT) | Licensed surveyor, local
Civiltest Pty Ltd |  | VP527574, VP527469 | Geotechnical investigation and design advice (PS-A) (VP527574) Geotechnical (Riverina CQA partner) (VP527469) | Not found: use website contact page | VP527574 Geotechnical: 12:00 pm Fri 16/10/2026 (AEDT) VP527469 Geotechnical: 12:00 pm Fri 23/10/2026 | civiltest.com.au; Mitcham, Mildura, Wodonga offices; Wodonga office
HARC (Blackburn VIC) |  | VP527574 | Floodplain modelling and hydraulic impact assessment (VP527574) | 03 9908 2160 | VP527574 Floodplain Modelling: 12:00 pm Fri 16/10/2026 (AEDT) | harc.com.au contact page
Provincial Geotechnical |  | VP527574 | Geotechnical investigation and design advice (PS-A) (VP527574) | Not found: use website contact page | VP527574 Geotechnical: 12:00 pm Fri 16/10/2026 (AEDT) | 11/10 draft had admin@pgvic.com.au (not confirmed)
Spiire (Bendigo office) |  | VP527574 | Civil design supervision and approval (RPE Vic, Civil) (VP527574) Supplementary survey and survey day rate (VP527574) | 03 5448 2500 | VP527574 Civil Supervision RPEV: 12:00 pm Fri 16/10/2026 (AEDT) VP527574 Survey: 12:00 pm Fri 16/10/2026 (AEDT) | 16 Bridge St Bendigo (2017 drawing); local content
APV Valuers & Asset Management |  | VP527277, VP527819 | Valuer: review and sign-off of transport and bridge asset valuations (VP527277) Valuation partner (comprehensive revaluation) (VP527819) | (08) 8311 3949 | VP527277 Valuation: 12:00 pm Wed 28/10/2026 VP527819 Valuation: 12:00 pm Wed 21/10/2026 | apv.net; directory listing, confirm
Australis Asset Advisory Group |  | VP527277, VP527819 | Valuer: review and sign-off of transport and bridge asset valuations (VP527277) Valuation partner (comprehensive revaluation) (VP527819) | Not found: use website contact page | VP527277 Valuation: 12:00 pm Wed 28/10/2026 VP527819 Valuation: 12:00 pm Wed 21/10/2026 | WALGA supplier listing
Infrastructure Management Group (IMG) |  | VP527277, VP527819 | Road network imaging and condition rating (VP527277) Field data capture (inventory and condition audit) (VP527819) | Not found: use website contact page | VP527277 Road Imaging Condition: 12:00 pm Wed 28/10/2026 VP527819 Condition Data Collection: 12:00 pm Wed 21/10/2026 | May tender MRC-2645 directly: ask. Same firm as VP527819 data capture; Did Council's 2021 inspection; likely to bid direct
Jeff Roorda & Associates (JRA) |  | VP527277, VP527819 | Valuer: review and sign-off of transport and bridge asset valuations (VP527277) Valuation partner (comprehensive revaluation) (VP527819) | Not found: use website contact page | VP527277 Valuation: 12:00 pm Wed 28/10/2026 VP527819 Valuation: 12:00 pm Wed 21/10/2026 | No website or contact found: confirm still trading
Pavement Management Services Pty Ltd (Seven Hills) | Regional Manager | VP527819 | Field data capture (inventory and condition audit) (VP527819) | 02 9674 9488 | VP527819 Condition Data Collection: 12:00 pm Wed 21/10/2026 | Confirm current entity and footpath capability
Aitken Rowe Testing Laboratories (East Wagga Wagga) |  | VP527469 | Geotechnical (Riverina CQA partner) (VP527469) | (02) 6939 5555 | VP527469 Geotechnical: 12:00 pm Fri 23/10/2026 | aitkenrowe.com.au
BESTEC |  | VP523438 | Street Lighting (VP523438) | Not found: use website contact page | VP523438 Street Lighting: 12:00 pm ACDT Fri 23/10/2026 | Office address to confirm
CIRQA |  | VP523438 | Traffic and Road Safety Audit (VP523438) | Not found: use website contact page | VP523438 Traffic and Road Safety Audit: 12:00 pm ACDT Fri 23/10/2026
Douglas Partners (Adelaide office) |  | VP523438 | Geotechnical (VP523438) | Not found: use website contact page | VP523438 Geotechnical: 12:00 pm ACDT Fri 23/10/2026
ExcelPlas Pty Ltd (Highett VIC) |  | VP527469 | Geosynthetics (NATA IQA testing, leak location surveys) (VP527469) | (03) 9532 2207 | VP527469 Geosynthetics: 12:00 pm Fri 23/10/2026 | Confirm NATA scope covers GCL and geotextile
GeoQ (QLD) |  | VP527469 | Geosynthetics (NATA IQA testing, leak location surveys) (VP527469) | Not found: use website contact page | VP527469 Geosynthetics: 12:00 pm Fri 23/10/2026 | Part B leak location only; verify business
Inland Geotechnical (East Wagga Wagga) |  | VP527469 | Geotechnical (Riverina CQA partner) (VP527469) | Not found: use website contact page | VP527469 Geotechnical: 12:00 pm Fri 23/10/2026
Lucid Consulting Engineers (Adelaide) |  | VP523438 | Street Lighting (VP523438) | (08) 8407 9700 | VP523438 Street Lighting: 12:00 pm ACDT Fri 23/10/2026
Steed Surveyors (Mount Barker) |  | VP523438 | Survey (VP523438) | (08) 8391 3000 | VP523438 Survey: 12:00 pm ACDT Fri 23/10/2026 | Local
TRI Australasia Pty Ltd | Benjamin Hart | VP527469 | Geosynthetics (NATA IQA testing, leak location surveys) (VP527469) | 0457 442 721 | VP527469 Geosynthetics: 12:00 pm Fri 23/10/2026 | Ask if they nominate a leak location partner
Wallbridge Gilbert Aztec (WGA) | Brenton Harris | VP523438 | Geotechnical (VP523438) | Not found: use website contact page | VP523438 Geotechnical: 12:00 pm ACDT Fri 23/10/2026 | May tender as lead designer: ask first
NTRO (formerly ARRB) |  | VP527277 | Road network imaging and condition rating (VP527277) | Not found: use website contact page | VP527277 Road Imaging Condition: 12:00 pm Wed 28/10/2026 | Confirm roadside, culvert and unsealed inventory coverage
Shepherd Services |  | VP527277 | Road network imaging and condition rating (VP527277) | Not found: use website contact page | VP527277 Road Imaging Condition: 12:00 pm Wed 28/10/2026 | Services not verified: check website first

## Read me
JCE outreach list, prepared 12/10/2026. Nothing has been sent.
Priority: 1 = due within 4 days (by Fri 16/10/2026); 2 = due 17/10 to 23/10; 3 = later.
Edit only the yellow Status column (drop-down: Sent, Replied, Quote received, Declined, Called, Bounced). Example: 'Sent' once emailed.
Email 'TBC - phone' means no address was found or confirmed: ring the number on the Missing emails sheet or use the firm website. Do not guess an address.
What to send: attach the RFQ PDF and the Quote Return Form named for that firm, plus the Dropbox tender files listed. One email per firm.
Firms asked for more than one bid have one row with each bid on its own line.